## Business Requirements Checklist
HILLS-07 WORK BREAKDOWN STRUCTURE | [8 empty] | USER ACCEPTANCE TESTING SECTION
TASK # | TASK | DESCRIPTION | SOLUTION DESIGN APPROACH | DEVELOPER | ESTIMATED TIME | ACTUAL TIME | PRIORITY | STATUS | TEST SCENARIO | TESTER | TEST RESULTS | TESTER COMMENTS
Injury Illness |  |  |  |  | (HRS)
1 | Requirement Gathering | [6 empty] | Not Started
1.1 | Technical Specifications | Specifying the tech stack, and what we need for it to work |  |  | 2 | 2 |  | Not Started
1.1.1 | Choose Tech Stack | Front end framework, css framework, backend languages, API's… |  |  | 2 | 2 |  | Not Started
1.1.2 | Learn Tech Stack | All group members must learn specified tech stack (React, Api's, UVR, Flask, etc. |  |  | 10 |  |  | Not Started
1.1.3 | Determine Project Scope | Ensure all primary tasks are able to be completed… maybe add enhancements in future. |  |  | 0.5 |  |  | Not Started
1.1.4 | Determine Test Cases | Determine ways that we will have to test our karoake webapp. |  |  | 1 |  |  | Not Started
1.1.5 | Complete Technical Specifications |  |  |  | 15.5 | 4 |  | Not Started
1.2 | Document Requirements | [6 empty] | Not Started
1.2.1 | Determine Git Flow |  |  |  | 0.5 |  |  | Not Started
1.2.2 | Determine team communications | Notion, Git, Discord |  |  | 0.5 | 0.5 |  | Not Started
1.2.3 | Complete Document Requirements |  |  |  | 1 | 0.5 |  | Not Started
2 | Develop Design Documents | [6 empty] | Not Started
2.1 | Develop Mid-fidelity Storyboard | Use Figma to develop a prototype research how to make elements clickable. |  |  | 5 |  |  | Not Started
2.2 | Develop MVC Model |  |  |  | 1.5 |  |  | Not Started
2.3 | Dataflow diagrams | develop DFD's -- outline how data flows within APP. |  |  | 3.5 |  |  | Not Started
2.4 | Risk Assessment | Find potential issues that may arise during the project and how to mitigate |  |  | 0.5 |  |  | Not Started
2.5 | Determine project schedule and deadlines |  |  |  | 2 |  |  | Not Started
2.x | Complete Design Requirements |  |  |  | 12.5 | 0 |  | Not Started
3 | Implementation | [6 empty] | Not Started
3.1 | GUI | Setup React |  |  | 20 |  |  | Not Started
3.1.1 | Code Landing Page |  |  |  | 8 |  |  | Not Started
3.1.1.1 | Code Search Bar | Make a functional search bar and able to send input to the system |  |  | 7
3.1.1.2 | Display Logo |  |  |  | 1
3.1.1.x | Finish GUI Implementation |  |  |  | 36
3.1.2 | Code Suggestions Page |  |  |  | 1
3.1.3 | Code Karaoke Page |  |  |  | 2 |  |  | Not Started
3.1.3 | Code Karaoke Page |  |  |  | 2
3.2 | Integrate UVR |  |  |  | 8 |  |  | Not Started
3.3 | Integrate Genius |  |  |  | 4 |  |  | Not Started
3.4 | Integrate LLM Api | Could be OpenAI or Llama |  |  | 6 |  |  | Not Started
3.5 | Setup FastAPI backend server |  |  |  | 2 |  |  | Not Started
3.6 | Setup Node.js backend |  |  |  | 4
3.x | Finish Implementation / Coding |  |  |  | 29 |  |  | Not Started
4 | Testing | [6 empty] | Not Started
4.1 | Test GUI functionality | Complete UAT, and Regression testing on the GUI |  |  | 4 |  |  | Not Started
4.2 | Test UVR functionality |  |  |  | 4 |  |  | Not Started
4.3 | Test Genius functionality and integration |  |  |  | 4
4.4 | Test LLM functionality/integration |  |  |  | 4 |  |  | Not Started
4.5 | Test Server functionality |  |  |  | 4 |  |  | Not Started
4.x | Finish testing |  |  |  | 20 |  |  | Not Started
5 | Deployment | [6 empty] | Not Started
5.1 | Configure Github actions |  |  |  | 1 |  |  | Not Started
5.x | Finish deployment |  |  |  | 1 |  |  | Not Started
6 | Documentation |  |  |  | 1 |  |  | Not Started
6.1 | Edit Readme |  |  |  | 1 |  |  | Not Started
6.2 | Write Project Report |  |  |  | 4 |  |  | Not Started
6.x | Complete Documents |  |  |  | 8 |  |  | Not Started

## KEYS - Do Not Delete
CHECKLIST KEYS – do not delete –
STATUS | PRIORITY | APPROVAL STATUS
Not Started | LOW | Submit for Approval
In Progress | MED | Submitted
Complete | HIGH | Approved
On Hold |  | Needs review
Overdue
Needs Testing
Needs Stakeholder Confirmation